## Pianificazione progetto
Gantt diagram
Note: 1 period = 1 week |  |  |  |  | Emphasize period | 1 |  |  | Plan duration | [6 empty] | Effective start | [5 empty] | % completion | [6 empty] | Effective (over plan) | [7 empty] | % completion (over plan)
ACTIVITY | START OF THE PLANNIN | DURATION OF THE PLANNING | EFFECTIVE START | EFFECTIVE DURATION | % COMPLETION | PERIODI
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Requirement Engineering | 1 | 2 | 1 | 2 | 100%
Development planning | 3 | 1 | 3 | 1 | 100%
Model Use Case | 4 | 1 | 4 | 1 | 100%
Model Mockup | 4 | 2 | 4 | 2 | 100%
Model Cockburn Tables | 5 | 2 | 5 | 3 | 100%
Model Analysis Class Diagram | 7 | 2 | 7 | 2 | 100%
Model Analysis Sequence Diagram | 8 | 2 | 8 | 3 | 100%
Analysis check | 10 | 1 | 10 | 1 | 100%
Model architecture design | 11 | 1 | 11 | 1 | 100%
Model Design Class Diagram | 12 | 3 | 12 | 4 | 100%
Model Design Sequence Diagram | 16 | 3 | 16 | 4 | 100%
Implementation | 20 | 4 | 20 | 6 | 100%
Testing | 26 | 3 | 26 | 3 | 100%
Release to the costumer | 29 | 1 | 29 | 1 | 100%